End-to-End Order to Delivery Process Flow

| Document Type: | Process Flow |
| --- | --- |
| Version: | 1.0 |
| Date: | March 19, 2026 |

## 1. Process Overview

This document describes the complete order lifecycle from initial customer inquiry through final delivery, including parallel processing streams that can execute simultaneously.

Process Duration Target: 20-30 business days (order capture to delivery)

## 2. Phase 1: Order Capture & Intake (Days 1-2)

2.1 Customer submits inquiry with preliminary specifications

2.2 Sales team creates quote and initial proposal

2.3 Customer reviews and approves quote

2.4 Order officially placed with signed agreement and initial payment (50% deposit)

## 3. Phase 2: Order Processing & Parallel Setup (Days 2-3)

3.1 Order entered into system and assigned unique order ID

PARALLEL STREAM A: Specification & Design

- Engineering team receives order specifications

- Detailed technical specifications developed

- Customer technical review meeting scheduled

PARALLEL STREAM B: Supply Planning

- Supply chain team analyzes Bill of Materials requirements

- Supplier evaluation and selection process initiated

- RFQs distributed to qualified suppliers

## 4. Phase 3: Design Review & Supplier Bidding (Days 3-5)

PARALLEL STREAM A: Specification Revision

- Customer receives draft specifications

- Technical review and revision cycles

- Final spec approval and signoff

- Generate Bill of Materials (BOM) - 30% invoice issued

PARALLEL STREAM B: Supplier Selection

- Supplier bids received and evaluated

- Cost and quality analysis completed

- Preferred suppliers selected

- Purchase orders issued to suppliers

## 5. Phase 4: Component Sourcing & Manufacturing Prep (Days 5-15)

PARALLEL STREAM A: Supply Chain Execution

- Suppliers manufacture/source components

- Delivery tracking and ETA management

- Components start arriving at warehouse

- Quality inspection and receiving process

- Defective items returned or replaced

- Components allocated to order batch

PARALLEL STREAM B: Manufacturing Planning

- Manufacturing schedule created based on component arrival

- Assembly bay allocated and prepared

- Assembly team trained on custom specifications

- Testing protocols finalized

- Quality checkpoints defined

## 6. Phase 5: Manufacturing & Testing (Days 12-22)

PARALLEL STREAM A: Assembly & Manufacturing

- Components picked from inventory

- Engine assembly begins (custom configuration)

- Assembly recorded in system with completion milestones

- In-process quality checks at each assembly stage

- Final assembly verification

PARALLEL STREAM B: Documentation & Shipping Prep

- Assembly documentation prepared

- Test procedures and checklists finalized

- Generate final invoice - 15% payment collected upon component receipt

- Shipping label and documentation prepared

- Customer notified of manufacturing status

## 7. Phase 6: Quality Testing & Validation (Days 20-25)

PARALLEL STREAM A: Engine Testing

- Performance testing executed

- Safety and compliance validation

- Test results documented

- Issues logged and resolved

- Final sign-off by QA team

PARALLEL STREAM B: Customer Acceptance

- Customer notified of testing completion

- Optional customer witness testing

- Customer acceptance documentation received

- Final adjustments if required

## 8. Phase 7: Delivery & Closure (Days 25-30)

PARALLEL STREAM A: Logistics

- Engine packaged for shipment

- Shipped via carrier with tracking

- Real-time delivery tracking provided to customer

- Delivery confirmation received

PARALLEL STREAM B: Financial Closure

- Final invoice issued (5% final payment upon delivery)

- Payment collected

- Accounts receivable reconciliation

- Supplier invoices processed and paid

## 9. Post-Delivery Activities (Days 25+)

9.1 Customer acknowledgment and sign-off on delivery

9.2 Product warranty activation

9.3 Customer satisfaction survey

9.4 Post-delivery support and troubleshooting

9.5 Performance metrics reported and archived

9.6 Lessons learned captured for future improvements

## 10. Critical Path Analysis

Critical Path = Longest sequence of dependent tasks

Day 1-2: Order Capture

Day 2-5: Design & Specification (can overlap with sourcing)

Day 2-15: Component Sourcing (longest-lead supplier path)

Day 12-22: Manufacturing (cannot start until components arrive)

Day 20-25: Testing (must complete before shipment)

Day 25-30: Delivery (fixed end point)

Optimization: Start sourcing immediately while specs finalize to reduce overall cycle time

## 11. Parallel Opportunities Summary

Specification & Design (Stream A) executes in parallel with Supply Planning (Stream B)

Supplier Selection (Stream B) executes in parallel with Design Reviews (Stream A)

Manufacturing Prep (Stream B) executes in parallel with Component Sourcing (Stream A)

Quality Testing (Stream A) can overlap with Shipping Prep (Stream B)

Logistics (Stream A) overlaps with Financial Closure (Stream B)

Total parallelization saves approximately 5-7 days compared to sequential processing

## 12. Key Milestones & Gating Items

Gate 1: Order Confirmation (after customer payment)

Gate 2: Final Specifications Approved (before BOM finalization)

Gate 3: All Components Received (before manufacturing start)

Gate 4: Testing Passed (before shipment)

Gate 5: Final Payment Received (before delivery)

Gate 6: Delivery Confirmed (order complete)